## AD Milestones
ProjectID | ProjectName | CustomerID | Customername | ProjectManager | PortifolioOwner | DesignEndDate | CUTEndDate | SITEndDate | UATEndDate | GoLiveDate | Status | ReasonForAR | PathToMoveGreen | Comments | PathToGreenDate | Type
1000131507 | TMNA AIM FBD ENDECA DEV | 1200950 | Toyota Motor Sales, U.S.A. Inc. | B,SenthilNathan | B, SenthilNathan | 2017-04-21 | 2017-06-02 | 2017-06-23 | 2017-06-30 | 2017-07-10 | Green |  |  |  |  | AD
1000175826 | TMNA AIM FBD CC PLSQL Rewrite | 1200950 | Toyota Motor Sales, U.S.A. Inc. | B,SenthilNathan | B, SenthilNathan | 2017-01-13 | 2017-03-31 | 2017-05-12 | 2017-05-19 | 2017-06-05 | Green |  |  |  |  | AD
1000173739 | TMNA AIM FBD DCM NSH Rewrite | 1200950 | Toyota Motor Sales, U.S.A. Inc. | B,SenthilNathan | B, SenthilNathan |  |  | 2017-06-19 | 2017-07-05 | 2017-08-10 | Amber | What is making it amber/red? – received EA conditional signoff . Junit to be closed before SIT closure ETC 06/13 What is the impact to schedule, and cost, if any?No Is there any scope changes? No | Vishal from EA has provided a conditional signoff for SIT. Review comments received on 5/23. Review comment fixed. Junit to be closed by ETC 06/13. |  | 2017-06-13 | AD
1000156087 | TMS CAPS CAD FBD DW Reporting | 1200950 | Toyota Motor Sales, U.S.A. Inc. | B,SenthilNathan | B, SenthilNathan | 2017-03-27 | 2017-05-29 | 2017-06-26 | 2017-07-10 | 2017-07-10 | Red | What is making it amber/red? Report development is not started due to unavailability of source (RPD) which is being taken up by ascent vendor team (6/19 reports are pending). What is the impact to schedule, and cost, if any? As of now No Is there any scope changes? No | Manish / Prasun are working with customer to put the project on hold due to delay in receiving the RPD changes ETA 06/16 |  | 2017-06-16 | AD
1000172752 | TMNA FBD TBDC CY17 BI Dev | 1230054 | Toyota Connected, Inc | B,SenthilNathan | B, SenthilNathan |  | 2017-06-13 |  | 2017-06-23 | 2017-06-28 | Green |  |  | Sprints are 2 Week Long. And Every Alternate Tuesday we have Sprint Demo. Sprint 2 Demo - May 16 Sprint 3 Demo - May 30 Sprint 4 Demo - June 13 |  | AD
1000166147 | TMS AFTERSALES FB T3 CY17 P3 | 1200950 | Toyota Motor Sales, U.S.A. Inc. | Badarinath,Shwetha | R, Rajagopal Rajesh |  |  |  |  | 2017-07-21 | Green |  |  |  |  | AD
1000124010 | TMS CAPS FB ASM MOB ITR 4 DEV | 1200950 | Toyota Motor Sales, U.S.A. Inc. | Badarinath,Shwetha | R, Rajagopal Rajesh |  | 2017-06-02 | 2017-06-23 |  | 2017-07-21 | Green |  |  |  |  | AD
1000153477 | TMS EAID FB CC REWRITE DEV | 1200950 | Toyota Motor Sales, U.S.A. Inc. | G,Vijayakumar | Purushothaman, Ravi |  | 2017-05-30 | 2017-06-05 | 2017-06-13 | 2017-06-19 | Green |  |  |  |  | AD
1000169060 | TMNA NAPO FB PHASE 4 INCEPTION | 1200950 | Toyota Motor Sales, U.S.A. Inc. | Thirupatti, Vinyagamoorthy | Kannan, Venkatesh |  |  |  |  | 2017-06-30 | Green | Only Inception |  | User Stories signoff 60% Complete , Rest in progress |  | AD
1000170944 | TMNA NAPO FB PHASE3 CONST L2.2 | 1200950 | Toyota Motor Sales, U.S.A. Inc. | Thirupatti, Vinyagamoorthy | Kannan, Venkatesh |  |  | 2017-06-14 | 2017-06-21 | 2017-06-23 | Green |  |  | Warranty Defects fix and SFT in progress |  | AD
1000170369 | TEMA FB QPRQIRPCR DEV - QPRQIR | 1222926 | Toyota Motor Engineering & Manufacturing | Lakshminarayana, Ravishankar | Rohit |  |  | 2017-04-21 | 2017-08-04 | 2017-08-11 | Amber | Replanning of UAT for QPR QIR. Timeline for QPR QIR go live moved to Aug due to customer dependencies. There is an impact on Overall timeline and cost and CP is expected to be ~ 21% | QPR QIR UAT scheduled from 6/12. Validation of week 1 UAT modules is completed. Validation of remaining modules by Cognizant SMEs to complete by 6/16. |  | 2017-06-16 | AD
1000170369 | TEMA FB QPRQIRPCR DEV - PCR | 1222926 | Toyota Motor Engineering & Manufacturing | Lakshminarayana, Ravishankar | Rohit |  |  | 2017-04-21 | 2017-06-02 | 2017-06-24 | Amber | Delay of 2 weeks in PCR UAT execution completion from 5/19 to 6/2.Go Live deferred From 6/11 to 6/24. | Toyota to resolve TS.com attachment handling issue by 6/16.3 critical PCR UAT fixes to complete by 6/12. |  | 2017-06-16 | AD
1000149036 | TMS AUT FB FTC REWRITE PHASE2 - DCM |  | Toyota Motor Sales, U.S.A. Inc. | Natarajan,Kirishnaanand | Purushothaman, Ravi | [5 empty] | Amber | What is making it amber/red? TESS 2.0 issues exists. Cutover date with TESS 2.0 is unknown and dependent on TESS 2.0 fixes. What is the impact to schedule, and cost, if any? No holding cost due to this delay. Resources moved to DOE project. No impact to CP due to TESS delay.. Once environment is available, PT and pending SIT to be resumed. | As a mitigation, no resources are being held for DCM-QA task. Resources are moved to DOE project. When the environment is available, PT resource alone needs to be on-boarded for 1 week to complete the pending tasks. |  |  | AD
1000175528 | Toyota -TMNA TOMS SUBSET Desig | 1200950 | Toyota Motor Sales, U.S.A. Inc. | Padhi,Suresh Kumar | Purushothaman, Ravi |  | 2017-06-23 | 2017-07-15 |  |  | Amber | What is making it amber/red? • Due to multiple enhancement challenges the Country restrictions related construction was delayed and Cycle 1 SIT is not moving faster. The Cycle 1 SIT completion is pushed by 1 week. What is the impact to schedule, and cost, if any? • Though there will be delay in Cycle 1 SIT, we are planning to cover the same by Cycle 2 SIT and give this to UAT by 07/15. Is there any scope changes? Yes. There is a scope change. | What is being done to bring it back to green & what is the date by which it will be green. • Project Team has got the necessary environments after talking with the AMS team and planing to complete the SIT and give the build to UAT in time. • 16th June 2017. | ( Iteration 3) | 2017-06-16 | AD
1000177951 | Toyota -TMNA DCM DAD Uplift | 1200950 | Toyota Motor Sales, U.S.A. Inc. | Padhi,Suresh Kumar | Purushothaman, Ravi | 2017-01-27 | 2017-06-23 | 2017-06-09 | 2017-06-23 |  | Amber | What is making it amber/red? • Due to 3 days delay in completing the Construction of Iteration 2 USe cases, the SIT execution start got delayed by 3 days. So, SIT execution will complete with a delay of 3 days. What is the impact to schedule, and cost, if any? • Though there will be delay of 3 days in Iteration 2 SIT completion, QA team has used these 3 days in the preparation of Iteration 3 Test case design and Dev team has already started on teh Iteration 3 Construction. So, there is no impact in Overall schedule duration of SIT completion of all the 3 iterations. Is there any scope changes? No. | What is being done to bring it back to green & what is the date by which it will be green. • QA team has used these 3 days in the preparation of Iteration 3 Test case design and Dev team has already started on the Iteration 3 Construction. • 16th June 2017. | Iteration 2 -Regression & pre-UAT to complete by end of June. Iteration 3 - Construction to complete by end of June. | 2017-06-16 | AD
1000175541 | Toyota -TMNA Plano Lease Car | 1200950 | Toyota Motor Sales, U.S.A. Inc. | Padhi,Suresh Kumar | Purushothaman, Ravi |  |  |  | 2017-06-30 |  | Green |  |  | We are getting an CR for scope addition. |  | AD
1000161614 | TMS EIM FBD IPLUS DEV | 1200950 | Toyota Motor Sales, U.S.A. Inc. | Mohamed, Nainar | B, SenthilNathan | 2016-10-31 | 2017-03-08 | 2017-05-29 | 2017-07-17 | 2017-07-21 | Red | What is making it amber/red? – Red due to delay in QA environment availability for Performance Testing and Report Comparison Testing from client end. Team is facing issues in Solr ingestion. Collections are revisited and memory issues was identified. What is the impact to schedule, and cost, if any? Yes.TMNA have recommended to go with Performance testing and UAT in parallel. Current timlines to be revisited post confirmation from TMNA. Is there any scope changes? No | SOX Reports - Report comparison testing started in DDC environment. Performance Testing to go in parallel with UAT to meet the timelines Performance testing for Phase - I was completed except ACtg06 and Accounting 09 is in progress for Phase -II NON SOX Reports - To mitigate the DDC environment delay, report comparison testing startd in DC1 environment for 1 year data. DDC environment was available. UI Domain was up for QA. PT Scripting started in QA environment. Memory issue to be taken to TMNA |  | 2017-06-14 | AD
1000162384 | TMNA AIM FBD IRM R4.0 | 1200950 | Toyota Motor Sales, U.S.A. Inc. | Raghupathy,Srinivas | B, SenthilNathan | 2017-05-26 | 2017-06-02 | 2017-06-09 | 2017-06-23 | 2017-06-26 | Green | Team is facing issues in Solr ingestion. Collections are revisited and memory issues was identified. | Report comparison testing started in DDC environment. |  |  | AD
1000170130 | TEMA Scalable Development - RAS | Samuel Dhyriam,Antony Sam Fran | Rohit | Samuel Dhyriam,Antony Sam Fran | Kalyanshetti, Rohit |  |  |  | 2017-05-31 |  | Green |  | Performance Testing to go in parallel with UAT to meet the timelines |  |  | AD
1000166400 | TEMA FB HCM DEV | 1222926 | Toyota Motor Engineering & Manufacturing | Samuel Dhyriam,Antony Sam Francis | Kalyanshetti, Rohit | [5 empty] | Amber | What is the impact to schedule, and cost, if any? Yes.TMNA have recommended to go with Performance testing and UAT in parallel. Current timlines to be revisited post confirmation from TMNA. | Performance testing for Phase - I was completed except ACtg06 and Accounting 09 is in progress for Phase -II |  |  | AD
1000156884 | TMS EIM FBD CSAP VSC DEV | 1200950 | Toyota Motor Sales, U.S.A. Inc. | A, Sridharan | B, SenthilNathan | 2017-02-06 | 2017-02-13 | 2017-06-19 | 2017-06-19 | 2017-09-01 | Green | Is there any scope changes? No | NON SOX Reports - |  |  | AD
1000164548 | TMS AUT FDM EIM PH4A DEV | 1200950 | Toyota Motor Sales, U.S.A. Inc. | A, Sridharan | B, SenthilNathan | 2017-03-31 | 2017-04-14 | 2017-04-24 | 2017-05-26 | 2017-06-09 | Green |  | To mitigate the DDC environment delay, report comparison testing startd in DC1 environment for 1 year data. |  |  | AD
1000166260 | TMS AIM FB OFFLINE RPT DEV | 1200950 | Toyota Motor Sales, U.S.A. Inc. | Rajendran, Janardhanan | B, SenthilNathan | 2017-06-30 | 2017-08-25 | 2017-09-22 | 2017-10-13 | 2017-10-27 | Green |  | DDC environment was available. UI Domain was up for QA. PT Scripting started in QA environment. |  |  | AD
1000168392 | TMS AIM VDW TTMS SIMPL DEV | 1200950 | Toyota Motor Sales, U.S.A. Inc. | A, Sridharan | B, SenthilNathan | 2016-08-26 | 2016-11-30 | 2017-02-28 | 2017-05-05 | 2017-06-09 | Green |  | Memory issue to be taken to TMNA |  |  | AD
1000164383 | TMS AFTERSALES FB T3 TQNET | 1200950 | Toyota Motor Sales, U.S.A. Inc. | Janardhanan, Pranila | R, Rajagopal Rajesh |  |  |  | 2017-06-01 | 2017-06-02 | GREEN |  |  | Got Go -Live Approval from business . Marking the status as GREEN |  | AD
1000163978 | TMS AFTERSALES FB T3 TGD DEV | 1200950 | Toyota Motor Sales, U.S.A. Inc. | Subramanian,Venkatesh | R, Rajagopal Rajesh |  | 2017-05-31 | 2017-06-30 |  |  | GREEN |  |  |  |  | AD
1000169551 | Toyota -TMNA DFA Workout TOPS - TOPS | Venkataraman,Prasanna | Purushothaman, Ravi | Venkataraman,Prasanna | Purushothaman, Ravi |  |  |  |  | 2017-04-20 | Green |  |  |  |  | AD
1000169551 | Toyota -TMNA DFA Workout TOPS - RIM | Venkataraman,Prasanna | Purushothaman, Ravi | Venkataraman,Prasanna | Purushothaman, Ravi |  |  |  |  | 2017-04-14 | Green |  |  |  |  | AD
1000169551 | Toyota -TMNA DFA Workout TOPS - Event Management | Venkataraman,Prasanna | Purushothaman, Ravi | Venkataraman,Prasanna | Purushothaman, Ravi |  | 2017-05-26 | 2017-05-26 | 2017-06-09 | 2017-06-16 | Green |  |  |  |  | AD
1000169551 | Toyota -TMNA DFA Workout TOPS - RADAR | Venkataraman,Prasanna | Purushothaman, Ravi | Venkataraman,Prasanna | Purushothaman, Ravi |  | 2017-05-12 | 2017-05-19 | 2017-06-09 | 2017-06-12 | Green |  |  |  |  | AD
1000164496 | TMS AUT FB TTMS Simplify Ph2 | Natarajan,Kirishnaanand | Purushothaman, Ravi | Natarajan,Kirishnaanand | Purushothaman, Ravi |  | 2017-06-30 | 2017-07-14 | 2017-07-28 | 2017-08-04 | Green | UAT was planned for completion by 5/31. Due to issues at ICL end, one use-case is pending. With this as known issue, Parallel validation phase has started per plan. |  |  |  | AD
1000195431 | TMS AUT FB FTC-DOE Integration | Natarajan,Kirishnaanand | Purushothaman, Ravi | Natarajan,Kirishnaanand | Purushothaman, Ravi | 2017-06-02 | 2017-08-11 | 2017-10-20 | 2017-11-10 | 2017-12-01 | Green | Verbal approval received for starting the construction and coding has started per plan. Formal email approval in-progress. |  |  |  | AD
1000169551 | Toyota -TMNA DFA Workout TOPS - Staff Master reports | Venkataraman,Prasanna | Purushothaman, Ravi | Venkataraman,Prasanna | Purushothaman, Ravi |  | 2017-06-30 | 2017-07-14 | 2017-07-28 | 2017-08-04 | Green |  |  |  |  | AD
1000186874 | TMNA AIM FBD QA DASHBOARD | B, SenthilNathan | B, SenthilNathan | B, SenthilNathan | B, SenthilNathan | 2017-03-02 | 2017-04-07 | 2017-04-21 | 2017-06-02 | 2017-06-02 | Amber | * What is making it amber/red? UAT signoff approval is pending from customer due to DAX function getting impacted at TMNA end. Next update from TMNA : 06/09. * What is the impact to schedule, and cost, if any? The delay in UAT approval might delay in golive date. CR shall be proposed for further delay on implementation if it impacts more than 2 weeks | Next update from TMNA : 06/09 PST |  | 2017-06-09 | AD