## Meeting Tracker
Meeting Tracker
Project Name
Meeting No | Date Of Meeting | Time ( Pacific Time) | Facilitator | Meeting Agenda | Attendees | Topics Discussed | Action Item Log | Decision Log | Issue Log | Risk Log

## Risk Log
Risk Log
<Application Name>
Risk ID | Description | Risk Impact | Risk Probability | Risk Exposure | Risk Owner | Date Risk Logged | Mitigation Plan | Current Status | Comments | Status | Date Closed | Reference
1
2
3
4 | [12 empty] | Active
5 | [12 empty] | Closed- Transferred to Issue Log
6 | [12 empty] | Abandoned
7
8
9
10
11
12
13
0
[5 empty] | Impact: | 1/2 - Minor |  | Probability: | 0.1 to 0.2 Low |  |  | 0.1 to 0.2 Low
[6 empty] | 3 - Important |  |  | 0.3 to 0.5 Medium |  |  | 0.3 to 0.5 Medium
[6 empty] | 4 - Significant |  |  | 0.6 to 0.9 High |  |  | 0.6 to 0.9 High
5 - Major
6 - Major Significance

## Action Item Log
LT
Action Item Log
Action item ID | Open Date | Reference/ Reported By | Functional Area | Action Required | Category | Responsible | Status | Baseline Due Date | Priority | Comments | Revised Due Date | Closed Date | Closed By
<Application Name>
1
2
3
4

## Issue Log
Issue Log
<Application Name>
Issue ID | Date when Identified | Issue Description | Issue Owner | Target Date for Closure | Actual Date for Closure | Current Status | Comments | Reference
1
2
Open
Assigned
In-Progress
Closed

## Decision Log
Decision Log
<Application Name>
Decision ID | Functional Area | Description of the Decision | Group Responsible for Deciding | Date for Decision | Current Status | Comments | Reference
1
2 | [7 empty] | Open
3 | [7 empty] | In-Progress
4 | [7 empty] | Approved
5 | [7 empty] | Rejected
6
7
8

## Agreements
TTMS Simplification - Agreement Log
Agreement Number | Agreement Date | Agreement Description | TLS Agreed By | I/S Agreed By | ICL Agreed By
1 | 2016-03-16 | 1) ICL will support SIT before November 1st 2016 as per the table in the attached document , 2) The data would be from the generator component, this data may not be passing all the business validations of ICL system, and the data could be manually generated. 3) ICL systems may not be ready for doing performance testing as per the timelines(in the attached document) , the same would be revisited around May -2016 time frame and evaluate ICL readiness for PT. 4) Starting Nov 1st 2016, ICL system will be available with full functionality and would be ready for UAT/Parallel/End to End testing with TTMS integration system. 5) Both ICL and TTMS are planning to go live is in April(first 2 weeks) | N/A | William Hie | Ginney Jhamb

## Daily status format (hidden)
Action Item Log
ID | Open Date | Action Required | Status | Due Date | Comments | Owner | Reference
1 | 2015-10-05 | Create Change request - New outbound (Pre-TVA interface) | Open | 2015-10-31 | New outbound interface discovered during elaboration. Current ETA files to ICL does not have this information. | William
2 | 2015-10-05 | Create Change request - New outbound (TCI order interface) | Open | 2015-10-31 | New outbound interface discovered during elaboration. Current ETA files to ICL does not have this information. | William
3 | 2015-10-12 | Test Design and Test Plan should be updated in the Traceability Matrix | Open | 2015-10-15 |  | Venkat | Mtg Minutes TTMS Simplification Internal discussion_10092015
4 | 2015-10-09 | TLS team need to setup a meeting with TdPR team on Monday (10/12) to confirm the legacy vessel number, PRI country code requirement. | Open | 2015-10-30 |  | Ming | Mtg Minutes TTMS Simplification Internal discussion_10092015
5 | 2015-10-14 | All Use Case documents to ne be renamed as “TMS integration technical requirement doc”. | Open | 2015-10-15 |  | Venket | Decision taken on TTMS Simplification: VDW Use case walkthrough
6 | 2015-10-14 | Angshuman need to move all the status reports from VOB to Share point | Open | 2015-10-31 |  | Angshuman | OCIO inception check list meeting on 10/14/15
7 | 2015-10-09 | Return to port code and current port code change are not sent to ICL by ETA.Travis to provide the ticket number to fix this issue | Open | TBD | 10/19/2015: Update from Travis There are 2 RFC’s created for this issue and the action item will still remain open until this RFC got implemented. ETA:TBD RFC VEH00055857 – Update Current VDC (Origin) in TMS table RFC VEH00055112 – ETA – Send the Current VDC (Origin) updates to ICL | Travis | TTMSFunctionalClarification and Parking Lot items
8 | 2015-10-01 | ICL to find out how to generate Vessel ETA/ Shipping Schedule/ Marine shipping report for those NAP specific vessels. | Open | TBD |  | Reza | TTMSFunctionalClarification and Parking Lot items
9 | 2015-10-01 | Venkat need to find out where we need to elaborate OTM trigger events versus ICL trigger events. | Open | TBD |  | Venkat | TTMSFunctionalClarification and Parking Lot items
10 | 2015-09-18 | Venkat need to do the followup the down stream impact for passing Vessel ETA with changing country code as "PRI". | Open | 2015-10-09 |  | Venkat | TTMSFunctionalClarification and Parking Lot items
11 | 2015-09-29 | SL# 6 requirement is in the Vessel ETA file layout but is not specified in the SOR/BRD. Mark has to take decision | Open | 2015-10-09 |  | Mark | TTMSFunctionalClarification and Parking Lot items
12 | 2015-09-14 | The report requirements are not very detailed in SOR.Angshuman need to setup a series of meetings for next few weeks and Vekat need to be ready with sample reports before the meeting. | Open | 2015-10-21 |  | Venkat/ Angshuman | TTMSFunctionalClarification and Parking Lot items
13 | 2015-09-14 | Dinesh need to check with EA (Selva\Deepak) whether we can point to secure external website through TESS or not | Open | 2015-10-21 |  | Dinesh | TTMSFunctionalClarification and Parking Lot items
14 | 2015-08-31 | Travis need to have a discussion with ICL to come up with estimated dates for retrieving the ETA from TCOSMOS pass to ICL. | Open | TBD |  | Travis | TTMSFunctionalClarification and Parking Lot items
15 | 2015-10-20 | For the SOX user management mainframe report, AMS need to check with consumers (Melanie) of the report, if same can be generated out of ICL systems. | Open | 2015-10-31 |  | Venkat | Mtg Minutes TTMS Team Elaboration processElaboration schedule plan_10202015
16 | 2015-10-21 | Include the following scenario's for UI performance testing: LOGIN through TESS vs. Direct LOGIN to ICL. | Open | TBD |  | Reza | Mtg Minutes TTMSElaboration schedule _Scope Management _10212015
17 | 2015-10-21 | Need to setup a meeting with ICL for conforming the dates in the project plan. | Open | 2015-10-30 |  | Angshuman | Mtg Minutes TTMSElaboration schedule _Scope Management _10212015
18 | 2015-10-21 | In Elaboration Schedule sheet, update the text as "TCI" in interface column(Columna 'C'), if the interface is applicable for TCI. | Open | 2015-10-26 |  | Venkat | Mtg Minutes TTMSElaboration schedule _Scope Management _10212015
19 | 2015-10-22 | As per the team’s suggestion (Both TMS & ICL), RAID document need to be updated and upload it once again in share point. | Open | 2015-10-27 |  | Sam/Angshuman | Mtg Minutes TTMS Team Raid-Meeting Efficiency-Transport Communications_10222015
20 | 2015-10-22 | Need to create project status dash board. | Open | 2015-10-28 |  | Angshuman | Mtg Minutes TTMS Team Raid-Meeting Efficiency-Transport Communications_10222015
21 | 2015-10-22 | Need to prepare weekly status report similar to PCPS status report format | Open | 2015-10-30 |  | Angshuman | Mtg Minutes TTMS Team Raid-Meeting Efficiency-Transport Communications_10222015
22 | 2015-10-22 | Need to move elaboration project related documents from Box to SharePoint | Open | 2015-10-30 |  | Angshuman | Mtg Minutes TTMS Team Raid-Meeting Efficiency-Transport Communications_10222015
23 | 2015-10-22 | Reza to share Consolidated elaboration Project plan with the ICL tech team and come back by Friday (Oct 30th) if any change | Open | 2015-10-30 |  | Reza | Mtg Minutes TTMS Team Raid-Meeting Efficiency-Transport Communications_10222015
24 | 2015-10-22 | Integration tech team to share Consolidated elaboration Project plan with their team and come back if any change by Friday(Oct 30th) | Open | 2015-10-30 |  | ICL Tech Team | Mtg Minutes TTMS Team Raid-Meeting Efficiency-Transport Communications_10222015
25 | 2015-10-22 | Expand ocean leg for export routes and Match Pay for processing carriers and Inspection carriers | Open | 2015-10-30 |  | Ming | Meeting tracker meeting number 1 on 10/22
26 | 2015-10-26 | Should ICL display the SAW GID in the screen for the vessel shipments? Also need to discuss about other information for Vessel details which needs to be displayed in the screen. | Open | 2015-10-30 |  | TLS | Meeting tracker meeting number 2 on 10/26
27 | 2015-10-26 | CBU units going to Mexico/Puerto Rico Currently does ETA pass to ICL the inventory, including vehicle information and TVA event? | Open | 2015-10-30 |  | Reza/Travis | Meeting tracker meeting number 2 on 10/26
28 | 2015-10-26 | Does ETA send dealer assignment to ICL after whole sale/ Retail < i.e. after vehicle moves to category G or H > | Open | 2015-10-30 |  | Travis | Meeting tracker meeting number 2 on 10/26
29 | 2015-10-27 | When the group gets deleted, how ETA system sending dealer un-assigned to ICL. | Open | 2015-11-06 |  | Travis | Meeting tracker meeting number 3 on 10/27

## Change Request
Organization Impacted
ID | Functional Area | Change description | Comments | Due Date | Responsible | Org1 | Org2 | Org3